## Slide 1
Level Four 408.04a
OHP #1
BEFORE THE ACTIVITY:
Searching for Information;
Elaborating a Plan;
Assigning Tasks; and
Holding a Planning Meeting.
DURING THE ACTIVITY:
Supervising
AFTER THE ACTIVITY:
Hold a debriefing/Post-Activity Meeting; and
Submit a final Report
PLANNING A GROUP ACTIVITY

## Slide 2
Level Four 408.04a
OHP #2
When Searching for Information, answer these questions:
WHAT is the nature of the activity?
WHEN is it scheduled to happen?
WHERE will it take place?
WHY is it important to hold this activity?
WHO is responsible?
BEFORE THE ACTIVITY
The 5 W’s

## Slide 3
Level Four 408.04a
OHP #3
ASSIGNING A TASK
As soon as you receive the green light, name an assistant (2IC) who will assist you in your task.
Delegate secondary tasks to subordinates. Do not try to do it all yourself.

## Slide 4
Level Four 408.04a
OHP #4
HOLDING A PLANNING MEETING
When you determine who your assistants are, meet with them and delegate the different tasks related to the activity.
Ensure they know exactly what they have to accomplish.
Keep them informed of all changes and ask them to keep you informed as well.
Plan a series of target dates for each task being delegated and ask them to provide you with a periodic report (verbal or written) on the progression of their work.